## Slide 1: Better Treatments for Breathlessness in Palliative and End of Life Care BETTER-B trial processes and delivery
BETTER-B is funded by the European Union’s Horizon2020 research and innovation programme under grant agreement No. 825319. The views expressed in this presentation are those of the author(s) and not necessarily those of the funders.
Project Manager: Dr Adejoke Oluyase
Cicely Saunders Institute, King’s College London
Follow us on twitter: #betterbreathe
www.better-breathe.eu

## Slide 2: DISCLOSURE
Name: Adejoke Oluyase ​
Affiliation: King’s College London
Relationships with for-profit and not-for-profit interests: ​ None
​
Grants/Research Support: Medical Research Foundation
Consulting fees: None
Other (including employment): None

## Slide 3: The BETTER-B Trial
Design: International, multicentre, Phase III, double-blind, randomised, placebo-controlled trial.
Funding: The European Union’s Horizon 2020 Research and Innovation Programme under grant agreement No. 825319.
​​
Participants: COPD, ILD patients with Modified Medical Research Council Dyspnoea Scale grade 3-4​ ​
Grade 3 (I stop for breath after walking about 100 yards or after a few mins on level ground) or​
Grade 4 (I am too breathless to leave the house or I am breathless when dressing or undressing) ​
Procedures: Randomised 1:1 to oral mirtazapine 15mg/day or placebo, assessments at baseline, day 7, 14, 28, 56, 180​​
Clinical end points (at 56 days)​​
‘Worst’ and ‘average’ breathlessness over the past 24 hours using NRS​​
Chronic Respiratory Questionnaire (CRQ)​​
Integrated Palliative care Outcome Scale (IPOS)​​
Hospital Anxiety and Depression Scale (HADS)​​
Qualitative interviews & health economics​

## Slide 4: BETTER-B Main Trial Objective
To determine whether mirtazapine (a repurposed medicine) is an effective treatment for the reduction of self-reported worst breathlessness (as measured by a numerical rating scale (NRS)) at 56 days post start of treatment compared to placebo in patients with COPD or ILD.​

## Slide 5: BETTER-B Sites
12 sites in Europe:
3 UK sites
3 Italian sites
3 German sites
2 Ireland sites
I Poland site
Parallel Study in Australia using the same protocol but sponsored by the University of Technology Sydney, funded by the NHMRC – European Union under Application ID: APP1170731.
Numbers recruited:
272 UK/EU participants (205 patients/67 caregivers)
28 Australia/New Zealand participants (20 patients/8 caregivers)

## Slide 6: BETTER-B Timeline
Aug 2018
Grant awarded
Jan 2019
Project started
Dec 2019
MHRA submission
Jan 2020
UK leaves EU (original planned opening)
Mar 2020
UK Covid lockdown
Nov/Dec 2020
First 3 sites
opened in UK
Feb 2021
1st patient randomised
May 2021
First Ireland
site opened
Jul/Sep 2021
German sites opened
Nov 2021
2 Italian sites opened
Apr 2022
1 Italian site opened
Mar 2021
6 month no cost extension
Sep 2022
1 Poland site opened
May 2023
6 month no
cost extension
Notes: At the initial stages of the Covid-19 pandemic, Italy, Germany and Poland were not accepting non-Covid applications which delayed our timelines. The trial was scheduled to open to recruitment in January 2020 but experienced delays due to issues with sourcing
of the IMP, IMP manufacturing and the impact of Covid-19.

## Slide 7: Sponsorship & contracting
Risk No. | Description of risk | Level of risk | WP(s) involved | Proposed risk-mitigation measures
1 | UK leaving the EU in 2019 (Brexit) – current uncertainty regarding UK legislative requirements and status of UK sponsor within EU post Brexit. | High | 2-5 | Co-sponsorship between KCL and UCD will ensure all regulatory and legislative requirements for clinical trial conduct will be met in both the EU and UK post Brexit.
2 | Implementation of Clinical Trials Regulation in 2019 across EU prior to start of Clinical Trial. | Low | 2,3 | Co-sponsor UCD based in EU will manage EU Portal requirements.

## Slide 8: Sponsorship & contracting
BETTER-B: clinical trial of an IMP, Clinical Trial Authorisation (CTA) Applications were submitted to medicines regulators in participating countries.
Different legal requirements in EU countries e.g co-sponsorship not allowed in Germany
* KCL could not be added to the CTA forms for European Sites
Ireland: KCL designated as having contractual responsibilities
Poland: KCL designated as having contractual responsibilities
Italy: KCL designated as having contractual responsibilities

## Slide 9: Regulatory & ethics submissions
Different systems e.g. own portals for uploading CTA
Lack of information in English
Use of fax!
Working with local PI/team

## Slide 10: Regulatory & ethics submissions
At the initial stages, regulatory authorities in Italy, Germany and Poland were not accepting non-Covid applications. Germany wasn’t submitted until Aug 2020 and Italy March 2021. Poland was submitted in May 2021.
CTA resubmission occurred in both Ireland and Germany to allow for UCD to be designated as the main sponsor.
In Italy, 4-month delay between CTA submission and trial approval due to complications in IMP arrangements post-Brexit (required 2 rounds of submission).
In Poland, 13 month delay between CTA submission and trial approval (required 4 rounds of submission)
Apart from the UK, ethics applications were delayed in the other EU countries as they prioritised Covid-related applications.

## Slide 11: Response times for CTA approval
Countries | Formal CTA timelines during trial | Actual CTA timelines during trial
Germany | 30 days | 46 days
Italy | 60 days | 65 days (provisional), 117 days (full)
Ireland | 25 days for first response, 60 days total | 45 days
Poland | 60 days | 13 months
UK | 60 days | 42 days

## Slide 12: Challenges experienced and mitigation measures
Challenges​ | Mitigation measures
Covid-19 and its recurrent waves​ ​ Participating countries de-prioritised non-Covid research​ Fear of infection by participants/reluctance to visit hospital ​ Staff diversion to Covid-related work​ Staff shortage/overworked staff​ UK R & I pause to recruitment ​ Remote clinics/closure of clinics ​ Trial eligibility criteria​ Brexit ​ Delays in receiving the IMP due to a worldwide shortage | Allowed for remote consent and follow-up Opened additional PICC sites at KCH and an addition site in Ireland. Applied for a 12 month no-cost extension Removed cardiovascular exclusion from protocol as this impacted recruitment Co-sponsorship between KCL and UCD Worked with Modepharma to source another supplier

## Slide 13: Other strategies to increase recruitment
Regular meetings with sites to provide support
Presentations to clinical teams at meetings
Rewarding good practice e.g monthly newsletter showcasing sites meeting their monthly targets.
Posters in clinics
Newsletters etc

## Slide 14: Translation
Participant-facing documents were translated (PIS, consent form, subject diary, GP letter).
Questionnaires were reviewed to check those that were translated and validated in other languages. Where these were not available, forward and backward translations were carried out.

## Slide 15
BETTER-B Translations
Documents to be translated = All participant-facing documents (PIL, consent form, questionnaires, subject diary, GP letter)
Local teams translated English master document into native language (forward translation)
Local teams made changes necessary for local ethics approval
e.g removal of collection of race/ethnicity data in Germany
Changes sent to Sponsor for approval

## Slide 16: BETTER-B Translations
Forward translated document translated into English (backward translation)
All translations completed by one team member, and reviewed by another team member
Sponsor compared backward translation to English master documents & checked certificates
Aim: ensure faithful translation to ensure patients received the correct information
Translation certificates for forward & backward translations

## Slide 17: IMP
Sourcing a product licenced in an EU country for no-deal Brexit
Absence of production staff & prioritisation of Home Office listed products
Increased storage costs
Post Brexit QP release & shipment
Notes: Due to Brexit, manufacturing authorisation of UK-based manufacturer was no longer accepted. Batch release for the EU can no longer take place in the UK

## Slide 18: Patient and Public Involvement (PPI)
PPI involvement from inception
Reviewing participant-facing documents
Shaping the language and content of the BETTER-B website
Co-design of dissemination strategy
Patient involvement in the TMG and TSC

## Slide 19: Key reflections
Cross-national research is important in developing the evidence base.​
The new EU Clinical Trials Information System (CTIS) is a co-ordinated system that should help future trials.​
BETTER-B question though central to Covid-19 was de-prioritised. Palliative care should be a core part of health emergency.​